## inscope
No | Requestor | Requestor Function | Type | Category | SubCategory | SKUs Applicable | Requirement | Justification (Why) | Threshold (Accept) | Goal(Design Target) | Priority | Scope | Additional Comments/Information | Ambiguity Score | Clarification Questions | Response
8 | Tracy Foo | Quality | Legacy | Quality Improvement & Serviceability | Sensor Feedback | CD1, CD2, Cleanout latch process | Improve feedback for cleanout/duplexer missing by adding a dedicated sensor and improving firmware feedback. Sensor should not be tied to other sensors. | 20220315(Sau Pin): Design improvement to Cleanout to prevent/limit twist implemented. Need final alignment with requestor 20210607 (Jeffrey/TH): Improved solution planned & to be verified in CD2; CD1 design as threshold/back-up, budget catered Is it possible to add conduct circuit to detect latch? plan prototype to improve cleanout latch process to reduce the issue. 20210617AQ: it would be very expensive to add cleanout sensor (estimate $0.8~1) | Accept - Threshold | Better than current Manhattan units. | MUST | inscope
9 | Tracy Foo | Quality | Legacy | Quality Improvement & Serviceability | Print System Reliability | Manhattan, Yeti, Marconi | Eliminate Print System Problem by identifying root cause and implementing fix to prevent field failures. | 20230307(SP): No reported incident. Will change status to "Green". 20221209(SP): To monitor until MC checkpoint 202210315(Sau Pin):This is on-going investigation in Manhattan. Will apply fix, if any and qualified 20210607 (Jeffrey): To follow up with Pock Chueng Current issue on Manhattan and Yeti. the current team need to continue investigate the unknown root cause. If identified then we look for opportunity to implement on Marconi. Pauline is working on it for Manhattan and Yeti. 20220118 (AQ, Boon Hock, Tracy, ZJ) the PSP taskforce is still working on this issue. We continue checking field return units. So far most of the returned units are recoverable therefore difficult to find out the root cause of the failure. May request more EE resource on this taskforce (to identify the EE support). | Accept - Threshold | Better than or equal to current Manhattan | HIGH WANT | inscope
11 | Tracy Foo | Quality | Legacy | Quality Improvement & Serviceability | Paper Handling | Manhattan, Marconi | Implement paper de-skew function so printer can correct skewed paper during pick and guide media to a straight path. | 202200316(SP): This is already in current Manhattan product.No change to Marconi program When Paper is skewed during pick, printer can move the media in and out and guide the media to a straight path into the paper path (Normal and Best) | Accept - Threshold | as per current Manhattan, Turn roller deskew and Feed roller deskew | WANT | inscope
22 | Itsushi Wakabayashi | Marketing | Legacy | Output paper tray | Output Paper Tray Capacity | Marconi Base, Marconi Hi | The printer should support an output paper tray capacity of 100 sheets for both Marconi Base and Marconi Hi SKUs while tilted left and right at 20 degrees during printing. | Output Management Test with LP2 Life Test units show same performance as Manhattan. Need to review Marconi Base LP1 testing result. Need to conduct RnD validation test for Base SKU to support up to 80 sheets. Manhattan Base can accommodate around 80 sheets without ME modification. To align with marketing to test up to 80 on Marconi Base. | 100 sheets for both Marconi Base and Marconi Hi | 100 sheets output paper tray capacity | HIGH WANT | inscope
23 | Itsushi Wakabayashi | Marketing | Legacy | Media Size | Media Size Supported |  | The printer must support the following media sizes: Letter, Legal, Government Legal, Executive, Statement, 3x5 in, 4x6 in, 5x7 in, 13x18 cm, 8x10 in, 10x15 cm, L, Photo 2L, Envelope (#10, Monarch, 5.5 bar), Card (3x5 in, 4x6 in, 5x8 in), Hagaki, 5x5, 4x5, and 4x12 inch HP branded photo media while tilted left and right at 20 degrees during printing. | Mech is able to support these media size. New media size added need to evaluated performance and accept as it is. Accept. | Support listed media sizes | Support listed media sizes | MUST | inscope
24 | Mandy Hagedorn | Marketing | Legacy | Media Sizes | Expanded Photo Media Handling | Marconi Base | The printer must support expanded photo media handling for 5x5 and 4x12 inch sizes for Marconi Base SKU while tilted left and right at 20 degrees during printing. | Marconi Base LP2 DET completed and able to support expanded photo media handling for 5x5 and 4x12. LP1 test with media still on-going. Follow Novelli solution. | Support expanded photo media handling for 5x5 and 4x12 inch sizes | Support expanded photo media handling for 5x5 and 4x12 inch sizes | Must | inscope
25 | Mandy Hagedorn | Marketing | Legacy | Feature | Simplex and Duplex Printing | ME Platform | Assess functional failure when printer is tilted left and right at 20 degrees during printing. Follow Novelli solution for simplex and duplex print on brochure and photo media. Wider bottom margin (0.50 inch) and less ink on first side, with UI changes for media type selection. | Follow Novelli solution and align with TME and Marketing to drop this. Novelli investigated duplex on 4x6 Photo Matte media and proposed UI changes for media type selection to avoid mech limitation issues. | Accept - Threshold | Follow Novelli solution | Must | inscope
26 | Ben / Ricker | OPS | Legacy | Quality Improvement & Serviceability | Print Quality | ME Platform | Remove LDV, change to 4HC. Print quality should be same as Malbec. Evaluate functional failure when printer is tilted left and right at 20 degrees during printing. Accept threshold for drop. | No change from Manhattan. Marconi has bigger swath height and printmode is more sensitive to linefeed error. LDV cannot be removed but parameter setting may be possible per vendor. | Accept - Threshold | Same as Manhattan | Not specified | inscope
28 | Celine Taccori | Design | Legacy | Feature | Quiet Mode | GxD | Quiet mode activation during printing must be instantaneous and result in a noticeable reduction in noise, confirmed by user perception. | Same as Manhattan/Malbec. Majority delivered in FW BR3 except trigger in middle of printing planned post BR3.1. User must hear difference when quiet mode is activated. | Accept - Threshold | Quiet mode should be instantaneous and hearable | Must | inscope
29 | Tracy Foo | Quality | Legacy | Quality Improvement & Serviceability | Printer Noise | ME Platform | Printer noise during operation must meet threshold as per Blue Angel item 153 activities, unless throughput increase is required. | No change from Manhattan. Follow-up on Acoustic Testing with Marconi units. Blue Angel is a goal, not a threshold, as it conflicts with throughput. | Accept - Threshold | Same as Manhattan | Must | inscope
30 | Tracy Foo | Quality | Legacy | Quality Improvement & Serviceability | PHA Rejection | ME Platform | PHA Rejection issue (62.80.A0): Find a fix to eliminate this issue. Workaround is to remove and re-install PHA. Monitor and implement animation prompt for re-seat as in Manhattan. | Issue reported during Manhattan launch. Root cause unknown. Animation prompt rolled out in Manhattan to reduce returns. Monitor and implement similar solution for Marconi. | Accept - Threshold | Better than or equal to current Manhattan | High Want | inscope
31 | Tracy Foo | Quality | Legacy | Customer Experience | Carriage Movement Lock | ME Platform | Improve carriage movement lock during transportation in moving vehicles. Solution should be better than Manhattan and prevent carriage-related returns. | Carriage related returns are top 3 for Mobile products. Current lock insufficient. Goal is better than Manhattan. No issues captured on user handling or vibration tests. | Accept - Threshold | Better than current Manhattan | Must | inscope
22 | Marketing | Marketing | New | Feature | Market Expansion |  | Expand Continuous Ink Supply System (CISS) profitable market share by targeting new customer segments. | To increase revenue and market penetration. | Achieve targeted market share growth in new segments. | Achieve targeted market share growth in new segments. | High | inscope
23 | Project Management | Project Management | New | Feature | Schedule and Investment Constraints |  | Adhere to constraints on schedule and investments, including SuperAmp PHA life at 65K pages. | To manage project risks and costs effectively. | Project milestones met within budget and schedule. | Project milestones met within budget and schedule. | High | inscope
24 | Product Management | Product Management | SIMILAR | Feature | Warranty, Throughput, Serviceability Optimization |  | Optimize warranty life to 80K pages, throughput to 25/20 ppm, serviceability of ink maintenance box, SMB solution, and PaaS schedule. | To balance performance, service, and market needs. | Performance and service targets met as per schedule. | Performance and service targets met as per schedule. | High | inscope
25 | Product Management | Product Management | SIMILAR | Feature | Ink Hosting and Page Yield |  | Flexibly support hosting 12K-CMYK ink and achieve trade page yield of at least 6K. | To allow adaptability in product offerings based on market conditions. | Product can support 12K-CMYK and meet page yield targets. | Product can support 12K-CMYK and meet page yield targets. | Medium | inscope